## Slide 1: FY27 Learning Plan Updates
October 15, 2026

## Slide 2
Learning Plan Results: Two projects are gaining traction; Two projects are still experiencing recruitment constraints and one project has withdrawn
MOMENTUM
01
PCIT(Parent Child Interactive Therapy) delivery and recruitment have improved; all children are now in school through a school-district partnership.
02
Staff changes and a stronger review of collected data have improved alignment and implementation.
CONSTRAINTS + DECISION
03
Recruiting four childcare centers to participate in their program remains a challenge.
04
Research parameters limit recruitment.
05
Project withdrawn.
PROP R • EARLY CHILDHOOD
03
Notes: Q1 Reporting is Due Today, Project 3-Operational/Recruitment Constraints

## Slide 3: Learning Plan Information
Monthly Progress
15 Minutes By 5th of Every Month
Reporting Included
-Staffing Changes
-Spending
- Programmatic Progress toward Outcomes
Themes Identified:
Communication
Role Clarification
Recruitment and Outreach
Data Quality and Reporting
Notes: !5 Minutes to minimize reporting burden and allow

## Slide 4: Project One
Background:
Multigenerational Project
Works with Unhoused Minors
Caregivers all female
FY26 Concerns:
Data Reliability
Participant Eligibility
Length of Services
MHB Support Provided:
Capacity Building: Match Services to Child
Determine Services Contracted Provider Could Provide
Progress:
All children enrolled in Early Childhood Program through Partnership with SLPS
Contracted Provider has Completed a 10-week Session of Parent-Child Interaction Therapy
$72,920
Notes: Projects-Alphabetical Order, Contracted Provider has had a transition in Staffing, Recruitment of Participants is occurring in Groups.

## Slide 5: Project Two
Background:
Accredited ECE Program
EHS/HS Program
30% of Childcare Staff Have 20+ Yrs at that Center
FY26 Concerns:
Internal Communication
Data Collection and Review
MHB Support Provided:
Capacity Building: Identify one Spokesperson, Engage CEO
Determine Evaluation Workflow
Progress:
Data Alignment is Present
Communication for Clarity has increased
Review of Children’s Data is Present for Service Intervention
$99,634
Notes: Documents Used, Review, One of the Staff Members Departed

## Slide 6: Project Three
Background:
Accredited ECE Program
EHS/HS Program
Training of Providers
FY26 Concerns:
Internal Communication
Data Collection and Review
Recruitment
MHB Support Provided:
Capacity Building: Identify one Spokesperson
Support Specialist with Role and Understanding of what was written to be implemented
Grant Management
Lack of Progress:
Recruitment of 4 Childcare Centers Continues to Be a Challenge
Previous Provider Training did not build Capacity in Region
Family Consent and Screening Follow-Up
Desire to Over Saturate Programs that are already working with other providers or providers who previously provided similar services with MHB
$100,000

## Slide 7: Project Four
Background:
University
Research Project
FY26 Concerns:
Communication
Recruitment
MHB Support Provided:
Capacity Building: Identify one Spokesperson
Provide Recruitment Places and Strategy (Eligibility Requirements)
Review of Control Group vs Intervention Group
Lack of Progress:
Recruitment
Participation
Service Model- Achievement
Screening Follow-Up
$80,517
Notes: Staff Capacity was reduced due to Learning Plan approach

## Slide 8: Project Five
Background:
University
FY26 Concerns:
Recruitment
Data
MHB Support Provided:
Provide Recruitment Places and Strategy(Eligibility Requirements)
Lack of Progress:
Recruitment
Participation
Withdrawn
Notes: UMSl

## Slide 9: Project Six – Not on Learning Plan
Background:
Support housing unstable youth
FY26 Concerns:
Communication
Data
MHB Support Provided:
Several meetings with leadership
System of Care site visit
Clarification of expectations
Updates:
Improved communication
Staff is active in System of Care
Project currently at capacity
Pending:
Work on evaluation requests:
  Outputs and outcomes need to be strengthened in logic model
  Need to add details about psychiatric service in Participant Data Workbook
$550,000

## Slide 10: Any Questions?